## Slide 1
ANNOTATED DOUGHNUT
Investment mix is concentrated on platform and data foundations
BOARDROOM INK / NATIVE EDITABLE
Chart: 
| Platform | Data | Adoption | Controls
Share | 38 | 27 | 21 | 14
100%
portfolio
Controls 14%
Adoption 21%
Data 27%
Platform 38%
Native chart data remains editable; labels and leaders are native PowerPoint objects.

## Slide 2
PHASED ROADMAP
Four gated phases convert strategy into an auditable scale decision
BOARDROOM INK / NATIVE EDITABLE
01 Discover Jul 2026
Align value, scope, and governance.
• Project charter • Value baseline
EXIT Scope and value baseline signed
02 Design Aug 2026
Define target process and solution.
• Solution blueprint • Control design
EXIT Design authority approval
03 Pilot Sep-Oct 2026
Prove operational and commercial evidence.
• Pilot release • Adoption evidence
EXIT Pilot thresholds achieved
04 Scale Nov-Dec 2026
Industrialize delivery and benefits tracking.
• Scale runbook • Benefits dashboard
EXIT SteerCo scale decision
G1
G2
G3
G4
TOTAL DURATION | JUL-DEC 2026 | SCALE DECISION AT G4

## Slide 3
GANTT TIMELINE
Pilot schedule remains on plan, with data migration on watch
BOARDROOM INK / NATIVE EDITABLE
TASK / DELIVERABLE
OWNER
Jul 2026
Aug 2026
Sep 2026
W1 01-08
W2 08-15
W3 15-22
W4 22-29
W5 29-05
W6 05-12
W7 12-19
W8 19-26
W9 26-02
W10 02-09
W11 09-16
W12 16-23
W13 23-30
Governance setup
PMO
Solution design
Architecture
Data migration
Data
Pilot build
Product
Adoption readiness
Change
TODAY
Planned
Actual
On track
Watch
Not assessed
Milestone
Today