## Slide 1
KPI / STATUS
Transformation value is on plan while cycle time remains at risk
BOARDROOM INK / NATIVE EDITABLE
K1 Run-rate value
8.4
$m
TARGET 8 $m VARIANCE +0.4
Validated by Finance
Q3 2026
K2 Adoption
74
%
TARGET 80 % VARIANCE -6
Six points below target
Aug 2026
K3 Cycle time
12.3
days
TARGET 10 days VARIANCE +2.3
Data handoffs are the constraint
Aug 2026
K4 Control pass rate
96
%
TARGET 95 % VARIANCE +1
Sample size 412
Aug 2026
On track
Watch
At risk
Not assessed

## Slide 2
MILESTONE TIMELINE
Six evidence-backed milestones define the path to scale approval
BOARDROOM INK / NATIVE EDITABLE
2026-07-01
2026-12-15
M1 Charter approved 2026-07-08 | PMO EVIDENCE Signed charter
M2 Blueprint signed 2026-08-05 | Architecture EVIDENCE Design authority minute
M3 Data rehearsal 2026-09-02 | Data EVIDENCE Reconciliation pack
M4 Pilot release 2026-10-01 | Product EVIDENCE Release record
M5 Adoption threshold 2026-11-05 | Change EVIDENCE Usage dashboard
M6 Scale decision 2026-12-10 | SteerCo EVIDENCE Decision log
On track
Watch
At risk
Not assessed

## Slide 3
RISK HEAT MAP
Data readiness concentrates the critical exposure in two cells
BOARDROOM INK / NATIVE EDITABLE
1
1
2
2
3
3
4
4
5
5
LIKELIHOOD →
IMPACT ↑
R6
R3
R4
R5
R2
R1
RISK REGISTER | ID / EXPOSURE / OWNER / MITIGATION
R1
Source data quality
L5 × I5 Data
Daily cleanse burn-down
R2
Interface latency
L4 × I5 Engineering
Performance war room
R3
SME availability
L4 × I4 Operations
Named alternates
R4
Training completion
L4 × I4 Change
Manager escalation
R5
Vendor access
L4 × I4 Security
Pre-approved access window
R6
Benefits attribution
L2 × I3 Finance
Reconcile baseline monthly

## Slide 4
RACI MATRIX
Single-point accountability is explicit across the pilot governance chain
BOARDROOM INK / NATIVE EDITABLE
ACTIVITY / DECISION | Sponsor | PMO | Product | Data | Change
Approve charter | A | R | C |  | 
Sign blueprint | A |  | R | C | 
Release pilot | A |  | R |  | C
Validate benefits | A | R |  | C | 
Approve scale | A | R | C |  | I
A
Accountable
R
Responsible
C
Consulted
I
Informed